## Home
PMP® ITTO Reference Workbook — PMBOK® Guide, 8th Edition
Inputs • Tools & Techniques • Outputs, organized by the seven Project Management Performance Domains
© 2026 Entrupedia — All Rights Reserved
PMI® Premier Authorized Training Partner (ATP) ¦ CR 1109248 ¦ Al Khuwair, Muscat, Sultanate of Oman
www.entrupedia.com ¦ laith@entrupedia.com
This workbook is proprietary copyrighted material of Entrupedia. It is provided for the personal study use of Entrupedia learners and licensees only. Reproduction, redistribution, resale, or removal of the Entrupedia copyright notice is strictly prohibited. This is a protected, read-only reference file; content and structure are locked to preserve accuracy for exam preparation.
At a Glance
PMBOK® Guide edition | 8th Edition
Performance Domains | 7
Processes (with ITTO) | 40
Project Management Focus Areas | 5 (Initiating, Planning, Executing, Monitoring & Controlling, Closing)
Contents
▸ Framework
▸ Governance
▸ Scope
▸ Schedule
▸ Finance
▸ Stakeholders
▸ Resources
▸ Risk
Disclaimer: “PMI®”, “PMBOK®” and “PMP®” are registered marks of the Project Management Institute, Inc. Content summarized from A Guide to the Project Management Body of Knowledge (PMBOK® Guide) – Eighth Edition for educational reference purposes.

## Framework
PMP® Process Framework — Performance Domains × Project Management Focus Areas (PMBOK® Guide, 8th Edition)
© 2026 Entrupedia ¦ PMI® Premier ATP
Performance Domain | Initiating | Planning | Executing | Monitoring and Controlling | Closing
Governance | • Initiate Project or Phase | • Integrate and Align Project Plans • Plan Sourcing Strategy | • Manage Project Execution • Manage Quality Assurance • Manage Project Knowledge | • Monitor and Control Project Performance • Assess and Implement Changes | • Close Project or Phase
Scope |  | • Plan Scope Management • Elicit and Analyze Requirements • Define Scope • Develop Scope Structure |  | • Monitor and Control Scope • Validate Scope
Schedule |  | • Plan Schedule Management • Develop Schedule |  | • Monitor and Control Schedule
Finance |  | • Plan Financial Management • Estimate Costs • Develop Budget |  | • Monitor and Control Finances
Stakeholders | • Identify Stakeholders | • Plan Stakeholder Engagement • Plan Communications Management | • Manage Stakeholder Engagement • Manage Communications | • Monitor Stakeholder Engagement • Monitor Communications
Resources |  | • Plan Resource Management • Estimate Resources | • Acquire Resources • Lead the Team | • Monitor and Control Resourcing
Risk |  | • Plan Risk Management • Identify Risks • Perform Risk Analysis • Plan Risk Responses | • Implement Risk Responses | • Monitor Risks
Totals
Performance Domains | 7
Processes | 40
Disclaimer: “PMI®”, “PMBOK®” and “PMP®” are registered marks of the Project Management Institute, Inc.

## Governance
Governance Performance Domain — ITTO Reference (PMBOK® Guide, 8th Edition)
© 2026 Entrupedia ¦ PMI® Premier ATP ¦ www.entrupedia.com
Initiate Project or Phase |  |  | Initiating
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Business documents • Business case • Benefits management plan 2. Agreements 3. Enterprise environmental factors 4. Organizational process assets | 1. Expert judgment 2. Data gathering • Brainstorming • Focus groups • Interviews 3. Interpersonal and team skills • Conflict management • Facilitation • Meeting management 4. Meetings 5. Responsibility assignment matrix 6. Project canvas | 1. Project charter 2. Assumption log
Integrate and Align Project Plans |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Outputs from other processes 3. Enterprise environmental factors 4. Organizational process assets | 1. Expert judgment 2. Data gathering • Brainstorming • Checklists • Focus groups • Interviews 3. Interpersonal and team skills • Conflict management • Facilitation • Meeting management 4. Meetings 5. Project canvas | 1. Project management plan
Plan Sourcing Strategy |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Project management plan • Scope management plan • Quality management plan • Scope baseline • Schedule management plan • Financial management plan • Resource management plan 3. Project documents • Milestone list • Requirements documentation • Requirements traceability matrix • Quality metrics • Resource requirements • Project team assignments • Risk register • Stakeholder register 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Market research 3. Make-or-buy analysis 4. Source selection analysis 5. Document analysis | 1. Sourcing strategy plan • Insourcing or outsourcing decisions • Source selection criteria
Manage Project Execution |  |  | Executing
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan (any component) 2. Project documents • Change log • Lessons learned register • Milestone list • Project communications • Project schedule • Requirements traceability matrix • Risk register • Risk report 3. Approved change requests 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Project management information system 3. Meetings • Daily coordination meetings | 1. Deliverables 2. Work performance data 3. Issue log 4. Change requests 5. Project management plan updates (any component) 6. Project document updates • Activity list • Assumption log • Lessons learned register • Requirements documentation • Risk register • Stakeholder register 7. Organizational process asset updates
Manage Quality Assurance |  |  | Executing
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan 2. Project documents (all components) 3. Organizational process assets • Policies • Procedures • Regulations | 1. Audits 2. Checklists 3. Data representation • Affinity diagrams • Cause-and-effect diagrams • Flowcharts 4. Decision-making 5. Problem-solving 6. Process improvement | 1. Quality reports 2. Change requests 3. Project management plan updates 4. Project document updates
Manage Project Knowledge |  |  | Executing
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan (all components) 2. Project documents • Lessons learned register • Project team assignments • Resource breakdown structure • Stakeholder register 3. Deliverables 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Knowledge management 3. Information management 4. After-action reviews 5. In-progress postmortems 6. Storytelling 7. Retrospective meetings 8. Interpersonal and team skills • Active listening • Facilitation • Leadership • Networking • Political awareness | 1. Lessons learned register 2. Project management plan updates (any component) 3. Organizational process asset updates
Monitor and Control Project Performance |  |  | Monitoring and Controlling
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan (any component) 2. Project documents • Assumption log • Basis of estimates • Cost forecasts • Issue log • Lessons learned register • Milestone list • Quality reports • Risk register • Risk report • Schedule forecasts 3. Work performance information 4. Agreements 5. Enterprise environmental factors 6. Organizational process assets | 1. Expert judgment 2. Data analysis • Alternative analysis • Cost-benefit analysis • Earned value analysis • Root cause analysis • Trend analysis • Variance analysis 3. Decision-making (Voting) 4. Meetings 5. Project dashboards 6. Visual controls 7. Information radiators | 1. Work performance reports 2. Change requests 3. Project management plan updates (any component) 4. Project document updates • Cost forecasts • Issue log • Lessons learned register • Risk register • Schedule forecasts
Assess and Implement Changes |  |  | Monitoring and Controlling
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Change management plan • Configuration management plan • Scope baseline • Schedule baseline • Cost baseline 2. Project documents • Basis of estimates • Change log • Requirements traceability matrix • Risk report 3. Work performance reports 4. Change requests 5. Enterprise environmental factors 6. Organizational process assets | 1. Expert judgment 2. Change control tools 3. Data analysis • Alternative analysis • Cost-benefit analysis 4. Decision-making • Voting • Autocratic decision making • Multicriteria decision analysis 5. Meetings 6. Integrated change control 7. Backlog management | 1. Approved change requests 2. Project management plan updates (any component) 3. Project document updates • Change log
Close Project or Phase |  |  | Closing
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Project management plan (all components) 3. Project documents • Assumption log • Basis of estimates • Change log • Issue log • Lessons learned register • Milestone list • Project communications • Quality control measurements • Quality reports • Requirements documentation • Risk register • Risk report 4. Accepted deliverables 5. Business documents • Business case • Benefits management plan 6. Agreements 7. Procurement documentation 8. Organizational process assets | 1. Expert judgment 2. Data analysis • Document analysis • Regression analysis • Trend analysis • Variance analysis 3. Meetings | 1. Project document updates (Lessons learned register) 2. Final product, service, or result transition 3. Final report 4. Organizational process asset updates
Disclaimer: “PMI®”, “PMBOK®” and “PMP®” are registered marks of the Project Management Institute, Inc. © 2026 Entrupedia — All Rights Reserved.

## Scope
Scope Performance Domain — ITTO Reference (PMBOK® Guide, 8th Edition)
© 2026 Entrupedia ¦ PMI® Premier ATP ¦ www.entrupedia.com
Plan Scope Management |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Project management plan 3. Project documents • Requirements documentation • Risk register • Stakeholder register 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Data gathering • Interviews • Focus groups • Questionnaires and surveys 3. Data analysis 4. Test and inspection planning | 1. Project management plan updates • Scope management plan • Requirements management plan
Elicit and Analyze Requirements |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Agreements 3. Business case 4. Project documents • Assumption log • Lessons learned register • Stakeholder register 5. Project management plan • Requirements management plan • Scope management plan 6. Enterprise environmental factors 7. Organizational process assets | 1. Expert judgment 2. Decision-making 3. Data gathering • Benchmarking • Brainstorming • Focus groups • Interviews • Questionnaires and surveys 4. Data analysis (Document analysis) 5. Data representation 6. Interpersonal and team skills (Nominal group) 7. Design thinking 8. Prioritization/ranking 9. Meetings | 1. Requirements documentation
Define Scope |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Assumption log 3. Project management plan 4. Requirements documentation 5. Enterprise environmental factors 6. Organizational process assets | 1. Expert judgment 2. Decision-making 3. Data analysis 4. Decomposition 5. Interpersonal and team skills (Facilitation) 6. Product analysis | 1. Project documents • Project scope statement • Requirements documentation
Develop Scope Structure |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan 2. Project documents • Project scope statement • Requirements documentation 3. Approved changes 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Brainstorming 3. Decomposition | 1. Scope baseline 2. Work breakdown structure (WBS) 3. WBS dictionary 4. User stories 5. Product backlog
Monitor and Control Scope |  |  | Monitoring and Controlling
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Scope management plan • Quality management plan 2. Project documents • Requirements documentation • Performance measurement baseline • Quality test and evaluation documents 3. Quality metrics 4. Approved change requests 5. Deliverables 6. Enterprise environmental factors 7. Organizational process assets | 1. Data analysis • Variance analysis • Trend analysis • Root cause analysis 2. Performance reviews 3. Audits and inspections 4. Testing/product evaluations 5. Data representations 6. Process automations | 1. Quality reports 2. Verified deliverables 3. Change requests 4. Quality control measurements 5. Project management plan updates • Scope management plan • Quality management plan 6. Project document updates • Requirements documentation • Lessons learned register 7. Work performance information
Validate Scope |  |  | Monitoring and Controlling
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project documents • Requirements documentation • Scope baseline • Quality reports • Work performance data • Quality control measurements 2. Verified deliverables 3. Enterprise environmental factors 4. Organizational process assets | 1. Data gathering 2. Data analysis 3. Inspection 4. Decision-making 5. Customer talks and tests 6. Process analysis 7. Review meetings | 1. Accepted deliverables 2. Change requests 3. Project document updates • Quality reports • Work performance information • Requirements documentation 4. Lessons learned updates
Disclaimer: “PMI®”, “PMBOK®” and “PMP®” are registered marks of the Project Management Institute, Inc. © 2026 Entrupedia — All Rights Reserved.

## Schedule
Schedule Performance Domain — ITTO Reference (PMBOK® Guide, 8th Edition)
© 2026 Entrupedia ¦ PMI® Premier ATP ¦ www.entrupedia.com
Plan Schedule Management |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Project management plan (Scope management plan) 3. Development approach 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Data analysis (Alternative analysis) 3. Meetings | 1. Project management plan updates (Schedule management plan)
Develop Schedule |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Project management plan (Scope management plan) 3. Development approach 4. Project documents • Activity attributes • Activity list • Assumption log • Basis of estimates • Duration estimates • Lessons learned register • Milestone list • Project schedule network diagrams • Project team assignments • Resource calendars • Resource requirements • Risk register 5. Agreements 6. Enterprise environmental factors 7. Organizational process assets | 1. Expert judgment 2. Decomposition 3. Rolling wave planning 4. Precedence diagramming method 5. Logical relationship • Leads and lags 6. Dependency determination and integration 7. Estimation techniques 8. Reserve analysis 9. Data analysis • What-if analysis • Simulation 10. Voting 11. Schedule network analysis 12. Schedule compression • Critical path method • Critical chain method 13. Resource optimization (Resource leveling) 14. Project management information system 15. Agile release planning | 1. Schedule baseline 2. Project schedule 3. Schedule data 4. Project calendars 5. Change requests 6. Project management plan updates • Schedule management plan 7. Project document updates • Activity list • Activity attributes • Assumption log • Basis of estimates • Duration estimates • Lessons learned register • Milestone list • Project schedule network diagrams • Resource requirements • Risk register 8. Agreements
Monitor and Control Schedule |  |  | Monitoring and Controlling
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Schedule management plan • Scope baseline • Performance measurement baseline 2. Product backlog 3. Project documents • Lessons learned register • Project calendars • Project schedule • Resource calendars • Risk register • Schedule data 4. Work performance data 5. Enterprise environmental factors 6. Organizational process assets | 1. Data analysis • Earned value analysis • Burnup/burndown chart • Performance reviews • Trend analysis • Variance analysis • What-if scenario analysis 2. Critical path method 3. Critical chain method 4. Project management information system 5. Resource optimization 6. Leads and lags 7. Schedule compression 8. Branch and bound 9. Velocity 10. Daily coordination meetings 11. Sprint reviews 12. Backlog refinement | 1. Work performance information 2. Schedule forecasts 3. Change requests 4. Project management plan updates • Schedule management plan • Schedule baseline • Cost baseline • Performance measurement baseline 5. Project document updates • Assumption log • Basis of estimates • Lessons learned register • Project schedule • Resource calendars • Risk register • Schedule data
Disclaimer: “PMI®”, “PMBOK®” and “PMP®” are registered marks of the Project Management Institute, Inc. © 2026 Entrupedia — All Rights Reserved.

## Finance
Finance Performance Domain — ITTO Reference (PMBOK® Guide, 8th Edition)
© 2026 Entrupedia ¦ PMI® Premier ATP ¦ www.entrupedia.com
Plan Financial Management |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Project management plan • Schedule management plan • Risk management plan 3. Project documents 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Data analysis (Alternative analysis) 3. Meetings | 1. Financial management plan 2. Funding strategy
Estimate Costs |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Quality management plan • Scope baseline 2. Project documents • Lessons learned register • Project schedule • Resource requirements • Risk register 3. Make-or-buy decisions 4. Work package estimation 5. Enterprise environmental factors 6. Organizational process assets | 1. Expert judgment 2. Analogous estimating 3. Parametric estimating 4. Bottom-up estimating 5. Multipoint estimating 6. Data analysis • Alternative analysis • Reserve analysis • Cost of quality 7. Project management information system 8. Decision-making (Voting) | 1. Cost estimates 2. Basis of estimates 3. Project document updates • Assumption log • Lessons learned register • Risk register
Develop Budget |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Financial management plan • Resource management plan • Scope baseline 2. Project documents • Basis of estimates • Cost estimates • Project schedule • Risk register 3. Business documents • Business case • Benefits management plan 4. Agreements 5. Enterprise environmental factors 6. Organizational process assets | 1. Expert judgment 2. Cost aggregation 3. Data analysis (Reserve analysis) 4. Historical information review 5. Funding limit reconciliation 6. Financing | 1. Cost baseline 2. Project funding requirements 3. Project document updates • Cost estimates • Project schedule • Risk register
Monitor and Control Finances |  |  | Monitoring and Controlling
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Financial management plan • Cost baseline • Performance measurement baseline 2. Project documents • Lessons learned register • Project funding requirements 3. Work performance data 4. Organizational process assets | 1. Expert judgment 2. Data analysis • Earned value analysis • Trend analysis • Reserve analysis 3. To-complete performance index 4. Project management information system | 1. Work performance information 2. Revenue and cost forecasts 3. Change requests 4. Funding proposals 5. Project management plan updates • Financial management plan • Cost baseline • Performance measurement baseline 6. Project document updates • Assumption log • Basis of estimates • Cost estimates • Lessons learned register • Risk register
Disclaimer: “PMI®”, “PMBOK®” and “PMP®” are registered marks of the Project Management Institute, Inc. © 2026 Entrupedia — All Rights Reserved.

## Stakeholders
Stakeholders Performance Domain — ITTO Reference (PMBOK® Guide, 8th Edition)
© 2026 Entrupedia ¦ PMI® Premier ATP ¦ www.entrupedia.com
Identify Stakeholders |  |  | Initiating
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Business documents • Business case • Benefits management plan 3. Project management plan • Communications management plan • Stakeholder engagement plan 4. Project documents • Change log • Issue log • Requirements documentation 5. Agreements 6. Enterprise environmental factors 7. Organizational process assets | 1. Expert judgment 2. Data gathering • Questionnaires and surveys • Brainstorming 3. Data analysis • Stakeholder analysis • Document analysis 4. Data representation (Stakeholder mapping/representation) 5. Meetings | 1. Stakeholder register 2. Change requests 3. Project management plan updates • Requirements management plan • Communications management plan • Risk management plan • Stakeholder engagement plan 4. Project document updates • Assumption log • Issue log • Risk register
Plan Stakeholder Engagement |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Project management plan • Resource management plan • Communications management plan • Risk management plan 3. Project documents • Assumption log • Change log • Issue log • Project schedule • Risk register • Stakeholder register 4. Agreements 5. Enterprise environmental factors 6. Organizational process assets | 1. Expert judgment 2. Data gathering (Benchmarking) 3. Data analysis • Assumption and constraint analysis • Root cause analysis 4. Decision-making (Prioritization/ranking) 5. Data representation • Mind mapping • Stakeholder engagement assessment matrix 6. Meetings | 1. Project management plan updates (Stakeholder engagement plan)
Plan Communications Management |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Project management plan • Resource management plan • Stakeholder engagement plan 3. Project documents • Requirements documentation • Stakeholder register 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Communication requirements analysis 3. Communication technology 4. Communication models 5. Communication methods 6. Interpersonal and team skills • Communication styles assessment • Political awareness • Cultural awareness 7. Data representation (Stakeholder engagement assessment matrix) 8. Meetings | 1. Project management plan updates • Communications management plan • Stakeholder engagement plan 2. Project document updates • Project schedule • Stakeholder register
Manage Stakeholder Engagement |  |  | Executing
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Communications management plan • Risk management plan • Stakeholder engagement plan • Change management plan 2. Project documents • Change log • Issue log • Lessons learned register • Stakeholder register • Risk register • Status report • Project schedule 3. Enterprise environmental factors 4. Organizational process assets | 1. Expert judgment 2. Communication skills (Feedback) 3. Interpersonal and team skills • Conflict management • Cultural awareness • Negotiation • Observation/conversation • Political awareness 4. Ground rules 5. Meetings | 1. Change requests 2. Project management plan updates • Communications management plan • Stakeholder engagement plan 3. Project document updates • Change log • Issue log • Lessons learned register • Stakeholder register
Manage Communications |  |  | Executing
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Resource management plan • Communications management plan • Stakeholder engagement plan 2. Project documents • Change log • Issue log • Lessons learned register • Quality report • Risk report • Stakeholder register 3. Work performance reports 4. Enterprise environmental factors 5. Organizational process assets | 1. Communication technology 2. Communication methods 3. Communication skills • Communication competence • Feedback • Nonverbal communication • Presentations 4. Project management information system 5. Project reporting 6. Interpersonal and team skills • Active listening • Conflict management • Cultural awareness • Meeting management • Networking • Political awareness 7. Meetings | 1. Project communications 2. Project management plan updates • Communications management plan • Stakeholder engagement plan 3. Project document updates • Issue log • Lessons learned register • Project schedule • Risk register • Stakeholder register 4. Organizational process asset updates
Monitor Stakeholder Engagement |  |  | Monitoring and Controlling
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Resource management plan • Communications management plan • Stakeholder engagement plan 2. Project documents • Issue log • Lessons learned register • Project communications • Risk register • Stakeholder register 3. Work performance data 4. Enterprise environmental factors 5. Organizational process assets | 1. Data analysis • Alternative analysis • Root cause analysis • Stakeholder analysis 2. Decision-making • Multicriteria decision analysis • Voting 3. Data representation (Stakeholder engagement assessment matrix) 4. Communication skills • Feedback • Presentations 5. Interpersonal and team skills • Active listening • Cultural awareness • Leadership • Networking • Political awareness 6. Meetings | 1. Work performance information 2. Change requests 3. Project management plan updates • Resource management plan • Communications management plan • Stakeholder engagement plan 4. Project document updates • Issue log • Lessons learned register • Risk register • Stakeholder register
Monitor Communications |  |  | Monitoring and Controlling
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Resource management plan • Communications management plan • Stakeholder engagement plan 2. Project documents • Issue log • Lessons learned register • Project communications 3. Work performance data 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Project management information system 3. Data representation (Stakeholder engagement assessment matrix) 4. Interpersonal and team skills (Observation/conversation) 5. Meetings | 1. Work performance information 2. Change requests 3. Project management plan updates • Communications management plan • Stakeholder engagement plan 4. Project document updates • Issue log • Lessons learned register • Stakeholder register
Disclaimer: “PMI®”, “PMBOK®” and “PMP®” are registered marks of the Project Management Institute, Inc. © 2026 Entrupedia — All Rights Reserved.

## Resources
Resources Performance Domain — ITTO Reference (PMBOK® Guide, 8th Edition)
© 2026 Entrupedia ¦ PMI® Premier ATP ¦ www.entrupedia.com
Plan Resource Management |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Project management plan • Quality management plan • Scope baseline 3. Project documents • Project schedule • Requirements documentation • Risk register • Stakeholder register 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Data gathering (Interviews) 3. Data analysis (SWOT analysis) 4. Data representation • Hierarchical charts • Responsibility assignment matrix • Text-oriented formats 5. Organizational theory 6. Meetings 7. Green human resource management 8. Resource-based view | 1. Project management plan updates (Resource management plan) 2. Team charter 3. Project document updates • Assumption log • Risk register
Estimate Resources |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Resource management plan • Schedule management plan • Scope baseline 2. Project documents • Activity attributes • Activity list • Assumption log • Cost estimates • Resource calendars • Risk register 3. Project schedule 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Bottom-up estimating 3. Analogous estimating 4. Parametric estimating 5. Data analysis (Alternative analysis) 6. Project management information system 7. Meetings 8. Data gathering (Interviews) 9. Artificial intelligence 10. Predictive analytics 11. Virtual reality 12. Augmented reality 13. Branch and bound 14. Genetic algorithms 15. Constructive cost model | 1. Resource requirements 2. Basis of estimates 3. Resource breakdown structure 4. Project document updates • Activity attributes • Assumption log • Lessons learned register • Risk register
Acquire Resources |  |  | Executing
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Resource management plan • Procurement management plan • Cost baseline 2. Project documents • Project schedule • Resource calendars • Resource requirements • Stakeholder register 3. Enterprise environmental factors 4. Organizational process assets | 1. Decision-making (Multicriteria decision analysis) 2. Interpersonal and team skills • Negotiation • Problem-solving 3. Preassignment 4. Virtual teams | 1. Physical or virtual resource assignments 2. Project team assignments 3. Resource calendars 4. Change requests 5. Project management plan updates • Resource management plan • Cost baseline 6. Project document updates • Lessons learned register • Project schedule • Resource breakdown structure • Resource requirements • Risk register • Stakeholder register 7. Enterprise environmental factor updates 8. Organizational process asset updates
Lead the Team |  |  | Executing
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan (Resource management plan) 2. Project documents • Issue log • Lessons learned register • Project schedule • Resource calendars • Team charter • Work performance reports • Team performance assessments • Project team assignments 3. Enterprise environmental factors 4. Organizational process assets | 1. Colocation 2. Virtual teams 3. Communication technology 4. Interpersonal and team skills • Conflict management • Influencing • Motivation • Negotiation • Team building • Decision-making • Critical thinking • Coaching and mentoring 5. Training 6. Problem-solving (Six Thinking Hats®) 7. Retrospectives 8. Recognition and rewards 9. Individual and team assessments | 1. Team performance assessments 2. Change requests 3. Project management plan updates • Resource management plan • Schedule baseline • Cost baseline 4. Project document updates • Issue log • Lessons learned register • Project schedule • Resource calendars • Team charter • Project team assignments 5. Enterprise environmental factor updates 6. Organizational process asset updates
Monitor and Control Resourcing |  |  | Monitoring and Controlling
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan (Resource management plan) 2. Project documents • Issue log • Lessons learned register • Physical or virtual resource assignments • Project schedule • Resource breakdown structure • Risk register 3. Work performance data 4. Agreements 5. Organizational process assets | 1. Data analysis • Alternative analysis • Cost-benefit analysis • Performance reviews • Trend analysis 2. Problem-solving 3. Interpersonal and team skills • Negotiation • Influencing 4. Project management information system 5. Value stream mapping 6. Continuous improvement 7. Theory of constraints 8. Control charts 9. Branch and bound | 1. Work performance information 2. Change requests 3. Project management plan updates • Resource management plan • Schedule baseline • Cost baseline 4. Project document updates • Assumption log • Issue log • Lessons learned register • Physical resource assignments • Resource breakdown structure • Risk register
Disclaimer: “PMI®”, “PMBOK®” and “PMP®” are registered marks of the Project Management Institute, Inc. © 2026 Entrupedia — All Rights Reserved.

## Risk
Risk Performance Domain — ITTO Reference (PMBOK® Guide, 8th Edition)
© 2026 Entrupedia ¦ PMI® Premier ATP ¦ www.entrupedia.com
Plan Risk Management |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project charter 2. Project management plan (all components) 3. Project documents (Stakeholder register) 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Data gathering (Interviews) 3. Data analysis (Stakeholder analysis) 4. Meetings | 1. Project management plan updates (Risk management plan)
Identify Risks |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Requirements management plan • Schedule management plan • Financial management plan • Quality management plan • Resource management plan • Risk management plan • Scope baseline • Schedule baseline • Cost baseline 2. Project documents • Assumption log • Cost estimates • Duration estimates • Issue log • Lessons learned register • Requirements documentation • Resource requirements • Stakeholder register 3. Agreements 4. Enterprise environmental factors 5. Organizational process assets | 1. Expert judgment 2. Data gathering • Brainstorming • Checklists • Interviews 3. Data analysis • Root cause analysis • Assumption and constraint analysis • SWOT analysis • Document analysis 4. Interpersonal and team skills (Facilitation) 5. Prompt lists 6. Meetings 7. Artificial intelligence | 1. Risk register 2. Risk report 3. Project document updates • Assumption log • Issue log • Lessons learned register
Perform Risk Analysis |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Risk management plan • Scope baseline • Schedule baseline • Cost baseline 2. Project documents • Assumption log • Cost estimates • Duration estimates • Resource requirements • Risk register • Stakeholder register 3. Enterprise environmental factors 4. Organizational process assets | 1. Expert judgment 2. Data gathering and analysis (Interviews) 3. Interpersonal and team skills (Facilitation) 4. Risk categorization 5. Data analysis • Risk probability and impact assessment • Simulations • Sensitivity analysis • Decision tree analysis • Influence diagrams 6. Data representation (Probability and impact matrix) | 1. Project document updates • Assumption log • Issue log • Risk register • Risk report
Plan Risk Responses |  |  | Planning
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan • Resource management plan • Risk management plan • Cost baseline 2. Project documents • Lessons learned register • Project schedule • Project team assignments • Resource calendars • Risk register • Risk report • Stakeholder register 3. Enterprise environmental factors 4. Organizational process assets | 1. Expert judgment 2. Data gathering (Interviews) 3. Interpersonal and team skills (Facilitation) 4. Strategies for threats 5. Strategies for opportunities 6. Contingent response strategies 7. Strategies for overall project risk 8. Data analysis • Alternative analysis • Cost-benefit analysis 9. Decision-making (Multicriteria decision analysis) | 1. Change requests 2. Project management plan updates • Schedule management plan • Financial management plan • Quality management plan • Resource management plan • Procurement management plan • Scope baseline • Schedule baseline • Cost baseline 3. Project document updates • Assumption log • Cost forecasts • Lessons learned register • Project schedule • Project team assignments • Risk register • Risk report
Implement Risk Responses |  |  | Executing
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan (Risk management plan) 2. Project documents • Lessons learned register • Risk register • Risk report 3. Organizational process assets | 1. Expert judgment 2. Interpersonal and team skills (Influencing) 3. Project management information system | 1. Change requests 2. Project document updates • Issue log • Lessons learned register • Project team assignments • Risk register • Risk report
Monitor Risks |  |  | Monitoring and Controlling
INPUTS | TOOLS & TECHNIQUES | OUTPUTS
1. Project management plan (Risk management plan) 2. Project documents • Issue log • Lessons learned register • Risk register • Risk report 3. Work performance data 4. Work performance reports | 1. Data analysis • Technical performance analysis • Reserve analysis 2. Audits 3. Meetings | 1. Work performance information 2. Change requests 3. Project management plan updates (any component) 4. Project document updates • Assumption log • Issue log • Lessons learned register • Risk register • Risk report 5. Organizational process asset updates
Disclaimer: “PMI®”, “PMBOK®” and “PMP®” are registered marks of the Project Management Institute, Inc. © 2026 Entrupedia — All Rights Reserved.